## RAID log
ID | Type | Title | Description | Owner | Status | Probability | Impact | Mitigation / action | Date raised | Last updated | Due date
R-001 | Risk | Vendor feed contract renewal may lapse before the new loader is live | The vendor contract ends 31 Oct. Without renewal the orders feed stops. | Jordan Lee | Open | Medium | High | Escalate the renewal to Procurement. | 2026-08-04 | 2026-08-20 | 2026-10-31
R-002 | Risk | Legacy and lakehouse sales figures may not reconcile before finance sign-off | Finance must sign off the reconciliation before cutover. | Priya Natarajan | Open | High | High | Daily reconciliation report; timezone handling under review. | 2026-08-18 | 2026-09-22 | 2026-10-10
R-003 | Risk | Key data engineer on leave during cutover week | Only one engineer knows the legacy export jobs well. | Sam Okafor | Open | Low | Medium | Pair on the cutover runbook in advance. | 2026-08-25 | 2026-09-01
A-001 | Assumption | Finance will provide the cost-center list by end of September | Needed to tag every job with a cost-center label. | Mei Tanaka | Open |  | Medium |  | 2026-09-02 | 2026-09-10 | 2026-09-30
A-002 | Assumption | Dashboard users can tolerate a 2-hour freshness window during migration | Agreed informally with the BI leads. | Alex Rivera | Open |  | Medium | Confirm in writing with BI leads. | 2026-09-08 | 2026-09-25
I-001 | Issue | Orders feed partitions arrive late on Mondays | Monday dashboards show partial orders until mid-morning. | Priya Natarajan | In progress |  | Medium | Late-partition alert and automatic backfill. | 2026-09-01 | 2026-09-16
I-002 | Issue | Oversized dev warehouse cluster is driving up cloud costs |  | Sam Okafor | Open |  | Low | Right-size the dev cluster. | 2026-09-03 | 2026-09-15
D-001 | Dependency | Security team approval of the new service accounts | The lakehouse jobs can't run in production without the new accounts. | Jordan Lee | Open |  | High | Request submitted 12 Sep. | 2026-09-12 | 2026-09-12 | 2026-10-15